## Slide 1
PLUGINLIVE
Infrastructure cost optimisation
Summary of all plans — Phase 0, Plan A, Plan B1, Plan B2, Plan C
VERSION
4.0 · consolidated
DATE
25 August 2026
PREPARED BY
Infrastructure / FinOps
DECISION OWNER
CTO
STATUS
For approval
INTERNAL — CONFIDENTIAL

## Slide 2
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 1 · PURPOSE AND FINANCIAL POSITION
The position today
Two hard constraints: everything stays in an India region, and performance must be no worse than today. All four options satisfy both — they differ by roughly ₹5,000 to ₹23,000 per month, and by an order of magnitude in migration risk.
Internal — Confidential · Version 4.0 · 25 August 2026
2
ORIGINAL RUN-RATE
₹1,27,600
before Phase 0
ALREADY BANKED
₹44,000
Phase 0, complete
CURRENT RUN-RATE
₹84,800
baseline for this paper
PLAN A TARGET
₹21,000
−75% versus today
ALTERNATIVES
₹26k–44k
B2 · C · B1
STAGE / OPTION | ₹ PER MONTH | VERSUS TODAY | STATUS
Original estate | 1,27,600 | — | Superseded
Phase 0 — duplicate PG14 estate removed | −44,000 | — | Complete
Current run-rate | 84,800 | baseline | Live
Plan A — re-shape on Oracle Cloud | ≈ 21,000 | −75% | Under appraisal
Plan B1 — Cloud Run, lift and shift | ≈ 44,000 | −48% | Under appraisal
Plan B2 — Cloud Run, after queue rewrite | ≈ 26,000 | −69% | Under appraisal
Plan C — Azure Container Apps, self-managed DB | ≈ 41,300 | −51% | Under appraisal

## Slide 3
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 2 · OPTIONS APPRAISAL
Four costed options
Internal — Confidential · Version 4.0 · 25 August 2026
3
OPTION A
Plan A — Oracle Cloud
₹21,000
7 weeks · moderate effort
— −75% versus today
— ₹8,488 saved in week 0
— No data migration
— Reversible at every step
OPTION B1
Plan B1 — Cloud Run
₹44,000
10 weeks · high effort
— −48% versus today
— Native scale-to-zero
— Workers held warm — ₹11,500/mo
— 10 GB DB + 160 GB media move
OPTION B2
Plan B2 — + queue rewrite
₹26,000
14 weeks · very high effort
— −69% versus today
— Workers scale to zero
— Requires BullMQ rewrite
— Still ₹5,000/mo worse than A
OPTION C
Plan C — Azure
₹41,300
9–12 weeks · high effort
— −51%; ₹27,000 fully optimised
— KEDA built in — no rewrite
— Same migration as Plan B
— Memory floor near ₹30,000

## Slide 4
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 2.1 · WHY NO MIGRATION TARGET REACHES ₹21,000
The rate that decides the outcome
The estate is memory-heavy and CPU-light — 44 GiB resident against 1.35 cores in use. The deciding figure is the price of one permanently resident unit of capacity: the nearest equivalent of an OCI baseline node, 4 OCPU and 24 GB, held warm for a month.
Internal — Confidential · Version 4.0 · 25 August 2026
4
PROVIDER | NEAREST EQUIVALENT SHAPE | ₹ / MONTH | × OCI
OCI Ampere A1 — current | 4 OCPU / 24 GB | 4,421 | 1.0×
AWS Graviton, ap-south-1 | m7g.xlarge — 4 vCPU / 16 GiB | ≈ 11,000 | 2.5×
DigitalOcean, Bangalore | General purpose — 4 vCPU / 16 GB | ≈ 11,100 | 2.5×
Azure VM, Central India | D4ps_v5 — 4 vCPU / 16 GiB | ≈ 12,200 | 2.8×
Azure Container Apps — idle | 4 vCPU / 24 GiB warm | ≈ 19,300 | 4.4×
Google Cloud Run — always on | 4 vCPU / 24 GiB warm | ≈ 41,300 | 9.3×
Memory is the constraint.
OCI Ampere A1 prices memory at ₹86.82 per GB-month. Every alternative charges ₹300 to ₹700 for the same gigabyte.
Compute is where rivals come closest, at 2–3×. Memory is where they are 5–10× dearer — and memory is what this estate consumes.
Screening rule: if a provider cannot price memory below roughly ₹150 per GB-month, it cannot reach Plan A — and the rest of the modelling is wasted effort.

## Slide 5
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 4 · EVIDENCE BASE
What the estate actually does
Measured from the live estate and the production database on 17 August 2026, with the cluster re-checked on 27 August.
Internal — Confidential · Version 4.0 · 25 August 2026
5
MEASUREMENT | VALUE | IMPLICATION
Assessment submissions, last 30 days | 648 (~21/day) | Peak hour was 32 submissions — one every 112 seconds
Hours with any activity | 251 of 720 (34.9%) | Two thirds of the month is completely idle
Kubernetes CPU in use | 1.35 of 20 cores | Nodes run at 2–11% utilisation
Memory in use | 44 of 120 GB | Memory is the binding cost driver, not CPU
Sum of pod CPU requests | ~6.5 cores | fast-api alone reserves 5× the cluster's real usage
Production database size | 10 GB | Held by a managed service costing ₹21,870/month
Open database connections | 213 | PgBouncer takes this to about 20
Block and boot storage | ~2,900 GB | One static-site VM carries a 500 GB boot volume
Container images in registry | 407 GB + 151 GB | No retention policy has ever run
verify-frame cold vs warm | 3.3 s → 8 ms | The exam path can never scale to zero — in any plan

## Slide 6
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 3 · COMPLETE, 17 AUGUST 2026
Phase 0 — already banked
Internal — Confidential · Version 4.0 · 25 August 2026
6
₹44,000
per month, removed
The database was cut over to pl-prod-pg16 on 31 July, but the previous PostgreSQL 14 system — two instances of 2 OCPU and 32 GB — kept running in parallel with nothing connected to it.
VERIFIED BEFORE DELETION
— Zero client connections; 2 inserts, 3 updates, 0 deletes over eight days
— Last row written 3 August versus 17 August on the live system
— Diverged by 295 students and 5,629 assignment records — a frozen snapshot
— Zero references across all ten namespaces
— After deletion: all pods running, no new restarts
ARCHIVED, BOTH SURVIVING
— Logical dump — 2.17 GB, verified at 2,603 objects
— Manual system backup — 1 GB, 35-day retention
— Side-fix: three read-only helper scripts had been returning stale production data since 3 August; all repointed

## Slide 7
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 5 · RE-SHAPE ON ORACLE CLOUD
Plan A — what changes
Everything stays on OCI, in Mumbai. The saving comes from matching capacity to measured load, and switching capacity off when it is genuinely not needed.
Internal — Confidential · Version 4.0 · 25 August 2026
7
TARGET ARCHITECTURE
— Production — OKE Basic (free control plane), two A1 4/24 baseline nodes, one preemptible calendar burst node, self-managed PostgreSQL 16 with PgBouncer
— Frontends — Object Storage behind the existing load balancer
— DEV and UAT — one VM each, database merged in, scheduled off nights and weekends
— Batch — parsers and normalisation on Container Instances, billed per second
THREE RULES BAKED INTO THE DESIGN
RULE 1
The exam path never sleeps
auth-node, student-node and fast-api stay warm during exam hours — 3.3 s cold against 8 ms warm is why.
RULE 2
App and database stay together
Documented N+1 patterns turn a 2 ms hop into 100 ms+ per page.
RULE 3
Capacity leads demand
Scale from the assessment schedule 20 minutes ahead, not from CPU metrics after the fact. Zero cold start.

## Slide 8
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 5 · DELIVERY SCHEDULE
Plan A — seven weeks, ₹84,800 → ₹21,000
Internal — Confidential · Version 4.0 · 25 August 2026
8
WHEN | WORK | SAVING | RUN-RATE AFTER
Week 0 | Raise pg16 backup retention 1 → 30 days. Resource Scheduler on DEV, UAT and the builder: off 20:00, on 08:00, weekdays | ₹8,488 | ₹76,300
Week 1 | Merge DEV and UAT database VMs into their app hosts · registry retention · block volumes VPU 10 → 0 · 7-day baseline | ₹10,300 | ₹66,000
Weeks 2–3 | Right-size pod requests to p95 + 20% · PodDisruptionBudgets · KEDA in report-only mode | enabler | ₹66,000
Week 4 | New OKE Basic cluster, 2-node pool on 50 GB boots · drain, DNS switch · static sites to Object Storage | ₹21,500 | ₹44,500
Weeks 5–6 | PgBouncer (213 → ~20 connections) · self-managed PG16 · timed restore test · cutover · 7-day soak | ₹17,449 | ₹27,000
Week 7 | Calendar scaler — burst node warm 20 min before each window · KEDA scale-to-zero on idle workers | ₹3–6,000 | ≈ ₹21,000
Weeks 0 and 1 are unconditional — they apply whichever option is chosen, and none of them touches the production data path.

## Slide 9
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 5.5 · COST BUILD-UP AND ENVIRONMENTS
Plan A — where the ₹21,000 goes
Internal — Confidential · Version 4.0 · 25 August 2026
9
COMPONENT | SHAPE | ₹ / MONTH
Baseline OKE nodes (2) | A1 4 OCPU / 24 GB each | 8,842
Calendar burst node | preemptible, ~40 h/month | 200
Self-managed PostgreSQL | A1 4/24 plus 100 GB | 4,421
DEV + UAT + builder | 3 VMs, scheduled 36% of hours | 4,774
OKE Basic control plane | — | 0
Frontends | Object Storage + existing LB | 0
Block storage + performance units | ~950 GB, VPU 0 except DB | 2,620
Images, storage, email, DNS, checks | — | 1,083
Plan A total | ±5% | ≈ 21,940
BY ENVIRONMENT
DEV
₹6,631 → ≈₹2,200
Merge the database VM into the app host; schedule off nights and weekends with a one-click override
UAT
₹7,673 → ≈₹2,500
Same consolidation and schedule, with an override for planned test windows
PROD
₹70,500 → ≈₹16,300
Right-size requests → OKE Basic with 2 nodes + burst → static sites to Object Storage → self-managed PG16

## Slide 10
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 5.3 · INSTRUMENTATION PREREQUISITES
Four gaps gate the schedule
Verified on the live cluster, 27 August. Prometheus, kube-state-metrics, node-exporter, Grafana, Loki, Promtail and metrics-server are already deployed in production — no new monitoring platform is needed. Four gaps remain, together costing ₹100–200 per month.
Internal — Confidential · Version 4.0 · 25 August 2026
10
PREREQUISITE | CURRENT STATE | GATES | WHY IT IS REQUIRED | COST
Alertmanager in production | Absent — UAT has it | Week 2 | Production drops from five worker nodes to two plus a burst node. Less headroom demands alerting, not less of it | ≈ ₹0
Prometheus retention 7 → 30 days | 7 days | Week 2 | Week 1 captures a 7-day baseline and weeks 2–3 right-size to p95 + 20%; at 7 days the evidence expires first | ≈ ₹70
PodDisruptionBudgets | None defined | Week 4 | Week 4 drains nodes one at a time; without a budget a drain can remove the last replica of a customer-facing API | ₹0
postgres_exporter | Absent | Weeks 5–6 | D-1 transfers backups and recovery to the team; connections, replication lag and WAL success must be visible first | ≈ ₹0
Not required: Grafana Alloy replaces a working Promtail and changes no cost line. OpenLens and Headlamp duplicate Grafana and kubectl. Terraform is worth capturing at the week-4 rebuild, not as a mid-migration import.

## Slide 11
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 7 · ALTERNATIVE
Plan B — Google Cloud Run, Mumbai
Request-driven containers, a managed database, no cluster to operate. The price depends entirely on whether the queue engine is also rewritten.
Internal — Confidential · Version 4.0 · 25 August 2026
11
B1 — LIFT AND SHIFT | ₹ / MONTH
Always-warm tier — auth, student, fast-api | 24,600
Queue workers held always-on | 11,500
Scale-to-zero tier | 700
Cloud SQL PostgreSQL — 2 vCPU / 8 GB | 10,000
Memorystore Redis — 1 GB | 2,000
Storage, registry, LB, egress, logging | 4,000
DEV + UAT — true scale-to-zero | 2,000
B1 total | ≈ 44,000
B2 — AFTER THE QUEUE REWRITE | ₹ / MONTH
Workers become request-driven via Pub/Sub push | −11,500
fast-api warm only in scheduled windows | −6,600
All other lines unchanged | —
B2 total | ≈ 26,000
The blocker that sets the price: BullMQ
Cloud Run bills a container only while it handles a request. A worker blocking on Redis is not handling one, so it needs CPU always allocated — a virtual machine at roughly twelve times the price. Escaping it means re-deriving retry, back-off and delayed-job semantics.
Migration: 10 to 14 weeks. The high-risk stages are the data platform — 10 GB by logical replication, 160 GB of media re-signed — and the queue rewrite. Rollback after the data moves is difficult.

## Slide 12
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 8 · ALTERNATIVE, SELF-MANAGED DATABASE
Plan C — Azure Container Apps, Central India
Costed against the live inventory: 20 API deployments, 12 frontends, four queue workers, measured resident memory per service.
Internal — Confidential · Version 4.0 · 25 August 2026
12
COMPONENT | ₹ / MONTH
Container Apps — always-warm APIs | 10,600
Container Apps — queue workers (KEDA to zero) | 800
Container Apps — scale-to-zero tier, 12 services | 5,500
PostgreSQL host — D2pds_v5, self-managed | 5,550
Database storage + backup target | 2,130
Redis Basic C1 · frontends · registry | 8,550
Log Analytics · media, egress, DNS, Key Vault | 3,900
DEV and UAT | 4,300
Plan C total | ≈ 41,300
WHERE IT BEATS CLOUD RUN
— Idle billing. A warm replica bills at roughly one-eighth the active rate; Cloud Run charges full price.
— KEDA is built in. BullMQ workers scale to zero with no queue rewrite — B2's saving without B2's risk.
WHERE IT STILL LOSES
— Memory bills flat at ₹690 per GiB whether idle or active; 44 GiB resident sets a floor near ₹30,000.
— Self-managing saves only ₹5,300 here against ₹17,449 under Plan A — and removes the “nothing to operate” benefit.
— Same migration exposure as Plan B; 9–12 weeks; difficult rollback.
Lean variant ≈ ₹27,000 with reserved compute, Static Web Apps Free, Redis C0, Basic Logs and cron-warmed fast-api.

## Slide 13
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 9.1–9.2 · PLATFORM AND REGION FEASIBILITY
Every other provider screened
Internal — Confidential · Version 4.0 · 25 August 2026
13
PLATFORM | INDIA REGION | ASSESSMENT
Alibaba Cloud | Withdrawn | India data centre closed in 2022–23. Fails the India requirement outright
Tencent Cloud | Mumbai | Rejected on procurement and sovereignty grounds, not price — student personal data on a Chinese-owned cloud will fail customer security review
IBM Cloud | Chennai classic only | No full multi-zone India region for the managed services needed; no Ampere-class pricing; thin local ecosystem
DigitalOcean | Bangalore only | Compute competitive at ~2.5× OCI, but memory near ₹700/GB-month — the memory bill alone would exceed ₹30,000. No in-country failover
Salesforce | n/a | Not an infrastructure provider — SaaS plus Heroku, priced per dyno above Cloud Run
Render · Neon | None | No India region at all; two options from the original proof-of-concept stack fail requirement 1
AWS · Azure · GCP | Mumbai / Central India | All viable on region. Costed as Plans B and C, or rejected on the rate in section 2.1 — between them and OCI sits a 2.5× to 9.3× gap

## Slide 14
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 9.3 · DATA-STORE FEASIBILITY
Vector databases cannot replace PostgreSQL
Measured in production on 27 August: about 104,000 embeddings in 1.7 GB, inside an 11 GB database that is otherwise students, assessments, assignments and scores.
Internal — Confidential · Version 4.0 · 25 August 2026
14
TABLE | SIZE | ROWS
institute.institutes_campuses | 1,380 MB | 86,903
admin.mongo_db_cities | 91 MB | 5,736
institute.degrees | 70 MB | 4,454
corporate.job_roles | 69 MB | 2,359
institute.streams | 64 MB | 4,078
Three smaller tables | ≈ 5 MB | ≈ 300
Total | ≈ 1.7 GB | ≈ 104,000
— No joins, no foreign keys, no transactions. They are similarity engines over embeddings — an additional store, never a substitute for the system of record.
— Cost. pgvector on the existing database costs nothing. Pinecone, Qdrant and Weaviate each start near ₹2,200–4,400 per month — 10–20% of the entire Plan A target — to serve 104,000 vectors.
— Region. Pinecone serverless has no India region, which fails requirement 1 outright.
— Correctness. Ranking is hybrid — taxonomy gate, trigram and vector fused in one query. Splitting the vectors out removes the family gate that fixed “nurse resembles accountant”.
— Direction of travel. Elasticsearch was just consolidated into PostgreSQL. Adding a vector store puts a data store back.
Revisit at roughly ten million vectors — the estate is two orders of magnitude away.
A cheaper win exists now: institutes_campuses holds ~16 KB per row, so halfvec or binary quantisation would shrink it with no new service.

## Slide 15
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 10 · DECISION REGISTER
Decisions to sign off
Internal — Confidential · Version 4.0 · 25 August 2026
15
REF | DECISION | OWNER | IF ACCEPTED | IF DECLINED
D-0 | Adopt Plan A, Plan B or Plan C | CTO | A → ₹21,000 | B → ₹26–44k · C → ₹27–41.3k
D-1 | Self-manage PostgreSQL — team owns backups and recovery for a 10 GB database | CTO | −₹17,449 | floor becomes ₹38,000
D-2 | Two baseline nodes with a calendar burst node, not three always on | Infra | −₹4,421 | ₹25,400
D-3 | Migrate to an OKE Basic cluster — new cluster, DNS cutover, one-way | Infra | −₹6,834 | ₹27,800
D-4 | DEV, UAT and builder off nights and weekends, with a wake-up override | Eng + QA | −₹8,488 | ₹29,500
D-5 | Rewrite BullMQ to Pub/Sub push — Plan B only; unnecessary under Plan C | Backend | −₹11,500 | B remains ₹44,000
D-6 | Move embeddings to a dedicated vector database — not recommended | CTO | +₹2,200–4,400 | ₹0 — pgvector retained

## Slide 16
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTIONS 11–12 · RISK REGISTER AND ROLLBACK
Risks and guardrails
Internal — Confidential · Version 4.0 · 25 August 2026
16
OPEN RISKS THAT GATE THE PLAN
HIGH
pg16 backup retention is 1 day
The only production database has a 24-hour restore window. Raise to 30 days before anything else
HIGH
Credentials in plain ConfigMaps
Cloud, AI and database credentials readable by any cluster user. Move to Secrets or OCI Vault
HIGH
Overnight CI depends on scheduled hosts
D-4 stops DEV, UAT and the builder at 20:00. Decide wake-on-demand or move jobs into working hours
MED
Backup success is not alerted
Alert on backup age and WAL archiving failure; a runbook is a D-1 deliverable
MED
Self-managed database ownership
Mitigated by a completed restore drill before cutover, not after
ACCEPTANCE CRITERIA FOR EVERY PRODUCTION CHANGE
— API p95 latency no more than 10% worse than the week-1 baseline
— Error and timeout rates do not increase
— No sustained node CPU above 70–75% after right-sizing
— No OOM kills, memory pressure or unexpected eviction
— Database connections below 70% of the configured limit
— Queue delay and processing time do not materially increase
— Login, assessment, scoring, proctoring and dashboard smoke tests pass
— Every capacity change has a written, tested rollback before it starts
Observation windows: 48 hours after a node drain · 7 days after the database cutover · 48 hours before deleting any replaced resource.

## Slide 17
PLUGINLIVE Infrastructure cost optimisation — summary of all plans
SECTION 14 · STATED LAST, AFTER THE EVIDENCE
Recommendation — approve Plan A
Internal — Confidential · Version 4.0 · 25 August 2026
17
Plan A costs about half of the best achievable Cloud Run outcome, delivers ₹8,488 in week 0 rather than week 10, needs no data migration, and is reversible at every step. Plan B2 reaches near-parity only after a queue rewrite; Plan C is the strongest migration option on risk, yet memory at ₹690 per GiB against 44 GiB resident sets a floor it cannot clear.
SEQUENCE | ACTION | OWNER | EFFECT
Immediately | Raise pl-prod-pg16 backup retention 1 → 30 days. Unconditional; it gates the database work under every option | Infra | risk fix
Week 0 | Resource Scheduler on DEV, UAT and the builder, with a wake-up override, after resolving the overnight CI dependency | Infra · Eng · QA | ₹8,488
Week 1 | Merge the DEV and UAT database hosts, registry retention, block volumes, seven-day baseline | Infra | ₹10,300
Before week 2 | Close the instrumentation gaps — Alertmanager in production and 30-day metric retention | Infra | enabler
Weeks 2–7 | Right-sizing, the OKE Basic rebuild, static sites, then the database cutover — each behind the guardrails | Infra · Backend · DBA | ₹45,000
What is being asked: decision D-0 — adopt Plan A. Weeks 0 and 1 are unconditional and can proceed while D-1 to D-4 are considered.